## Incident Register
Incident ID | Date reported | Business area | Location/site | Category | Severity | Status | Summary | Root cause | Customer impact | Estimated cost (EUR) | Corrective action | Owner | Due date
INC-0101 | 2026-01-08 | IT Services | Cloud | Service disruption | Critical | Resolved | Payment gateway outage for three hours across online channels | Third-party supplier outage | Customers unable to pay online | 48000 | Add secondary gateway and automatic failover | Deji Okafor | 2026-01-31
INC-0102 | 2026-01-13 | Customer Services | Dublin HQ | Service disruption | Low | Closed | Brief website slowness during a traffic spike | Traffic spike | Minor, pages loaded slowly | 0 | Enable autoscaling on the web tier | Deji Okafor | 2026-02-03
INC-0103 | 2026-01-19 | Manufacturing | Cork Plant | Quality | High | Closed | Batch deviation on production line 2 | Calibration drift on sensor | Batch quarantined, no shipment | 12000 | Recalibrate sensor and add weekly checks | Aoife Byrne | 2026-02-09
INC-0104 | 2026-01-27 | Claims Operations | London Office | Financial control | High | Resolved | Duplicate supplier payment issued | Manual process gap | Recovered in full, no loss | 0 | Add automated duplicate-payment check | Cian Nolan | 2026-02-17
INC-0105 | 2026-02-03 | Facilities Management | Belfast Office | Safety | High | Resolved | Slip hazard from a roof leak in the stairwell | Failed roof seal | One near-miss, no injury | 6000 | Repair roof and apply wet-floor protocol | Frank Moss | 2026-02-24
INC-0106 | 2026-02-10 | Logistics | Naas DC | Supply chain | Medium | Closed | Key supplier missed a delivery window | Supplier capacity issue | Minor stock gap | 2000 | Add a second source for the affected line | Emma Ryan | 2026-03-03
INC-0107 | 2026-02-14 | Retail Network | Naas DC | Service disruption | High | Resolved | Warehouse management system down during peak dispatch | Third-party supplier outage | Delayed deliveries to 40 stores | 22000 | Review supplier SLA and add manual dispatch fallback | Emma Ryan | 2026-03-07
INC-0108 | 2026-02-18 | Regulatory Affairs | Dublin HQ | Compliance | High | Resolved | Regulatory return submitted late | Ownership unclear | Regulator notified, no penalty |  | Assign a named owner and set calendar reminders | Hannah Doyle | 2026-03-11
INC-0109 | 2026-02-22 | Customer Services | Dublin HQ | Customer escalation | Medium | Closed | Complaint about a repeated billing error | System defect | One customer, goodwill credit applied | 300 | Fix the billing rule and monitor | Grace Patel | 2026-03-15
INC-0110 | 2026-02-28 | IT Services | Cloud | Data & security | Critical | Resolved | Phishing email led to one credential compromise | Human error | Account isolated, no data loss confirmed | 5000 | Reset credentials, run phishing training, enforce MFA | Deji Okafor | 2026-03-21
INC-0111 | 2026-03-05 | Manufacturing | Cork Plant | Quality | Medium | Resolved | Labelling error on packaged units | Manual data entry error | Rework required | 3000 | Add barcode verification at packing | Aoife Byrne | 2026-03-26
INC-0112 | 2026-03-11 | Facilities Management | Galway Site | Facilities | Low | Closed | HVAC intermittent fault in the office | Ageing equipment | Comfort only | 1500 | Service the unit and plan replacement | Frank Moss | 2026-04-01
INC-0113 | 2026-03-18 | Retail Network | Naas DC | Facilities | Medium | Closed | Chiller unit failure in the stockroom | Compressor fault | Some chilled stock lost | 5200 | Replace compressor and add a temperature alarm | Frank Moss | 2026-04-08
INC-0114 | 2026-03-24 | Operations | Naas DC | Safety | Critical | Resolved | Forklift collision with racking | Operator training gap | No injury, stock damage | 18000 | Run refresher training and segregate pedestrian traffic | Cian Nolan | 2026-04-14
INC-0115 | 2026-03-30 | Claims Operations | London Office | Financial control | Medium | In progress | Claims reserve mis-posted to the ledger | Data entry error | Corrected in ledger |  | Add a reconciliation control | Cian Nolan | 2026-04-22
INC-0116 | 2026-04-02 | Manufacturing | Galway Site | Quality | High | In progress | Out-of-spec temperature during storage | HVAC fault | Product on hold pending review | 9000 | Repair HVAC and add temperature alarms | Grace Patel | 2026-04-25
INC-0117 | 2026-04-09 | Logistics | Limerick Depot | Supply chain | High | Resolved | Container held at port, materials delayed | Customs documentation error | Production slowed for two days | 14000 | Pre-clear customs documentation for future shipments | Emma Ryan | 2026-04-30
INC-0118 | 2026-04-15 | Regulatory Affairs | London Office | Compliance | Medium | In progress | Inspection observation on record-keeping | Process not documented | Action plan requested |  | Document the SOP and train staff | Hannah Doyle | 2026-05-08
INC-0119 | 2026-04-22 | Operations | Dublin HQ | Service disruption | High | In progress | Telephony platform dropped inbound calls for two hours | Third-party supplier outage | Missed customer calls, SLA breach | 15000 | Migrate to redundant SIP trunks | Deji Okafor | 2026-05-15
INC-0120 | 2026-04-29 | Customer Services | Remote | Customer escalation | High | In progress | Cluster of complaints after a service change | Poor change communication | Multiple customers affected |  | Issue a communications plan and run a root cause review | Grace Patel | 2026-05-22
INC-0121 | 2026-05-06 | IT Services | Cloud | Data & security | High | In progress | Misconfigured share exposed an internal folder | Configuration error | Internal only, contained |  | Correct permissions and run an access review | Deji Okafor | 2026-05-29
INC-0122 | 2026-05-09 | Manufacturing | Cork Plant | Quality | Medium | Open | Repeat labelling error on line 3 | Manual data entry error | Rework required | 3500 | Extend barcode verification to line 3 | Aoife Byrne | 2026-06-02
INC-0123 | 2026-05-13 | Facilities Management | Sligo Facility | Facilities | Medium | Resolved | Water ingress in the storeroom | Blocked gutter | Minor stock damage | 2200 | Clear gutters and set an inspection schedule | Frank Moss | 2026-06-05
INC-0124 | 2026-05-20 | Operations | Naas DC | Safety | High | In progress | Near-miss: pedestrian in a vehicle lane | Operator training gap | No injury |  | Install physical barriers between traffic and walkways | Cian Nolan | 2026-06-12
INC-0125 | 2026-05-27 | Claims Operations | Remote | Financial control | High | Open | Exception in month-end reconciliation | Under investigation | Reporting delay |  | Investigate and strengthen controls | Cian Nolan | 2026-06-19
INC-0126 | 2026-06-04 | Regulatory Affairs | Dublin HQ | Compliance | High | Open | Consent records incomplete for an audit sample | Under investigation | Potential finding |  | Remediate records and run a gap analysis | Hannah Doyle | 2026-06-27
INC-0127 | 2026-06-11 | Facilities Management | Belfast Office | Facilities | Low | Open | Lighting failure in the car park | Failed fitting | None | 600 | Replace the failed fittings | Frank Moss | 2026-07-04
INC-0128 | 2026-06-18 | IT Services | Cloud | Service disruption | Critical | Open | Identity provider outage blocked staff sign-in | Under investigation | Staff unable to access core apps for 90 minutes |  | Awaiting root cause; interim access steps documented | Deji Okafor | 2026-07-10
INC-0129 | 2026-06-25 | Logistics | Naas DC | Supply chain | Medium | Open | Repeat supplier delivery shortfall | Supplier capacity issue | Stock gap on two lines | 2500 | Escalate the supplier review and dual source | Emma Ryan | 2026-07-18
INC-0130 | 2026-07-01 | Manufacturing | Galway Site | Quality | Low | Open | Minor cosmetic defect flagged by QC | Tooling wear | None, caught before shipment | 800 | Replace tooling on schedule | Grace Patel | 2026-07-24
INC-0131 | 2026-07-08 | Facilities Management | Sligo Facility | Safety | Medium | Open | Blocked fire exit reported | Poor housekeeping | None | 500 | Clear the exit and add a weekly audit | Frank Moss | 2026-08-01
INC-0132 | 2026-07-15 | Housing Services | Dublin HQ | Customer escalation | Medium | Open | Tenant escalation on repair delays | Contractor backlog | Several tenants affected |  | Clear the backlog and agree an SLA with the contractor | Hannah Doyle | 2026-08-07
INC-0133 | 2026-07-21 | Logistics | Limerick Depot | Service disruption | Medium | Open | Route planning tool unavailable, manual routing used | Third-party supplier outage | Later deliveries, no data loss | 4000 | Confirm the supplier remediation plan | Emma Ryan | 2026-08-08
INC-0134 | 2026-07-24 | IT Services | Cloud | Data & security | Medium | Open | Unusual sign-in flagged and blocked | Under investigation | None confirmed |  | Confirm false positive and review alert tuning | Deji Okafor | 2026-08-16

## Notes
About this file
Purpose | Sample incident register for the Operational Incident Intelligence Agent build-along (Microsoft × Codec).
Data | Synthetic. All incidents, names, sites and figures are invented for enablement and contain no real or personal data.
Data as at | 29 July 2026. 'Overdue' means the due date has passed while status is still Open or In progress.
Severity | Critical, High, Medium, Low. Definitions are in the Incident Management & Triage Policy.
Status | Open, In progress, Resolved, Closed. Definitions are in the policy.
Estimated cost | In euro. A blank means the cost was not recorded, not zero.
Root cause | 'Under investigation' means the root cause is not yet confirmed.
Cross-reference | Incident IDs match the write-ups in Example Incident Reports for eight of these incidents.